

**Gloucestershire Badminton – Moving Forward Together – Development Plan 2018 - 19**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Start | Finish | Lead Person(s) | Monitor/Support | Actions/Outcomes | Review |
| Communication and Marketing | June 2018 | September 2018 | Ian Woolway | Becky Pantaney  Sol Griffiths | - new website design and plan  - directors to meet and agree content  - CPD workshop on website usage and management  - launch | -website established with content re Community, County and PC in place  - discussed the need to keep updated as regularly as possible |
| Player development and recruitment | July 2018 | Ongoing | Mike Griffiths  James Siddle | Andrew Woolway | -secondary school teaching and learning initiative (pilot)  -talent spotting achieved through attendance and support of grass root competitive events  -increase number of KS2 meet and compete opportunities to include coaching element – monthly | -pilot initiative completed with eight secondary schools with positive evaluations from participants  -county coach representatives attendance of events much improved  -KS2 Meet and Compete more sessions held but attendance inconsistent. In response to this calendar of dates to be issued in September with sessions held at different venues to possibly attract more players. |
| Community/County Liaison Programme | September 2018 | Ongoing | Sol Griffiths  Becky Pantaney | Mike Griffiths  Andrew Woolway | -completion of coach volunteer visits for 2018-19  -CPD provision for active coaches and volunteers  -financial support towards obtaining coaching awards | -partnership coaches identified and link visits completed to Balcarras, GL1, Marling and Falcons. Pittville visit to be arranged – Sol Griffiths |

Review performed by directors – May 2019

* Partially completed and work in progress
* Achieved