Gloucestershire Badminton – Moving Forward Together – Draft Development Plan 2019 - 20

| Activity | Start | Finish | Lead Person(s) | Monitor/Support | Actions/Outcomes | Review |
| --- | --- | --- | --- | --- | --- | --- |
| Secondary Schools Initiative – support of in lesson and out of hours provision | September 2018 | Ongoing | Mike Griffiths Sol Griffiths | Becky Pantaney Campbell Wilson | -CPD and in lesson support for teaching of badminton in six secondary schools -support in establishment of out of hours learning -maintain and develop links between participating schools and Badminton Gloucestershire | May 2020 |
| County Competition | October 2019 | May 2020 | Andrew Woolway Ian Woolway | James Siddle Sol Griffiths | -Enter teams in the following: South West League U18; Shires U20 -Provide a programme of friendly matches for U16 – Saturday morning players | January 2020 |
| KS 2 – Meet and Compete initiative | September 2018 | Ongoing | James Siddle Mike Griffiths | Ian Woolway Campbell Wilson | -issue a calendar of sessions together with descriptor of initiative and session content -improve marketing of the initiative linking in with SGO’s to promote in primary schools -liaise with BE re its programme of primary development to identify potential players/participants | March 2020 |
| Playing/development opportunities for girls. | September 2019 | September 2020 | Becky Pantaney Ian Woolway | Sol Griffiths Andrew Woolway | -coaches to attend school games/community events to observe and identify possible candidates for further development -inclusion of at least one girls only event in the community calendar of events 2019 -20 | January 2020 |

Directors – Badminton Gloucestershire 10th May 2019